## Survey
# | Questions | Answers
Preparation (Level 1)
1-1 | Have you (the department's CIO) communicated the vision to consolidate IT infrastructure at the Technology Agency facilities? | <Select Yes or No>
1-2 | Has a Project Manager for the migration/consolidation identified and assigned? | <Select Yes Requistion In Process or No>
1-2a | Project Manager's Name | <name>
1-2b | Project Manager's e-mail address | <email address>
1-2c | Project Manager's phone number | <phone number>
1-3 | Have you established a team to collect the inventory? | Yes
1-4 | Have you established an approach for collecting the inventory? | Yes
1-5 | If you have not established an approach and a team, when do you expect to complete? | <enter expected completion date MM/YY>
Baseline and Initial Assessment (Level 2)
2-1 | Have you completed an inventory of your department's mission critical and public facing applications? | <select value>
2-1a | If not completed, estimate % complete | 0%
2-1b | If not completed, when do you plan to complete the inventory? | <enter expected completion date MM/YY>
2-1c | If complete, please provide a list of Mission Critical and Public Facing Applications | <complete columns B-H of the "MC-PF Applications" Tab; include one record for each instance (DR vs. Production) of each Mission Critical and Public Facing application>
2-2 | Have you assessed your mission critical applications and identified a target location (e.g. OTech, FDC etc.) ? | <Select Yes or No and complete columns I-K of the "MC-PF Applications" Tab
2-3 | Have you completed an inventory of your department's data centers/server rooms? | <select value>
2-3a | If not completed, estimate % complete | 0%
2-3b | If not completed, when do you plan to complete the inventory? | <enter expected completion date MM/YY>
2-3c | If completed, provide a list of all data centers | <Complete columns B-L of the "Data Centers" Tab for each data center/server room>
2-4 | Have you completed an inventory of your department's applications and equipment at your data centers? | <select value>
2-4a | If not completed, estimate % complete | 0%
2-4b | If not completed, when do you plan to complete the inventory? | <enter expected completion date MM/YY>
2-4c | If completed, please provide a summary of equipment in each data center | <complete columns K and L of the "Data Centers" Tab (do not include Mission Critical and Public Facing Applications)>
2-5 | Have you assessed your applications and servers and identified a target location (e.g. OTech, FDC etc.) ? | <Select Yes or No>
2-5a | if your assessment is complete, enter the estimated number of physical servers you plan to migrate to OTech | <enter number of servers>
2-5b | if your assessment is complete, enter the estimated number of physical servers you plan to migrate to FDC | <enter number of servers>
2-5c | if your assessment is complete, enter the estimated number of physical servers you plan to migrate to another Technology Agency approved Data Center | <enter number of servers>
Planning (Level 3)
3-1 | Level 3A - If the inventory of all Mission Critical and Public Facing Applications is complete, how much progress have you made in developing a plan to migrate these applications?
3-1a | Prioritized and sequenced applications | <Select Yes or No>
3-1b | Selected migration approach for each application | <Select Yes or No>
3-1c | Completed high level design and infrastructure (e.g. network) assessment | <Select Yes or No>
3-1d | Captured resource requirements (equipment and personnel) | <Select Yes or No>
3-1e | Budget approved | <Select Yes or No>
3-1f | Defined migration dates | <Select Yes or No>
3-1g | Submitted plan to the Technology Agency for review | <Select Yes or No>
3-1h | Received agreement and approval from the Technology Agency | <Select Yes or No>
3-2 | If not completed, when do you plan to complete the migration plan? | <enter expected completion date MM/YY>
3-3 | If completed, does it incorporate all major refreshes and new applications deployments occurring at Technology Agency approved facilities? | <Select Yes or No>
3-4 | If completed, please provide a copy of the schedule and key information for each Mission Critical and Public Facing application | <complete columns L-Q of the "MC-PF Applications" Tab for each Mission Critical and Public Facing application>
3-5 | Level 3B - If the inventory of all data centers and applications complete, how much progress have you made in developing a migration plan?
3-5a | Prioritized and sequenced applications | <Select Yes or No>
3-5b | Selected migration approach for each application | <Select Yes or No>
3-5c | Completed high level design and infrastructure (e.g. network) assessment | <Select Yes or No>
3-5d | Captured resource requirements (equipment and personnel) | <Select Yes or No>
3-5e | Budget approved | <Select Yes or No>
3-5f | Defined migration dates | <Select Yes or No>
3-5g | Submitted plan to the Technology Agency for review | <Select Yes or No>
3-5h | Received agreement/approval from the Technology Agency | <Select Yes or No>
3-6 | If not completed, when do you plan to complete the migration plan? | <enter expected completion date MM/YY>
3-7 | If completed, does it incorporate all major refreshes and new applications deployments occurring at Technology Agency approved facilities? | <Select Yes or No>
3-8 | If completed, please provide a copy of the schedule and a summary of the migration plan | <complete columns M-P of the "Data Centers" tab and columns B-P of the "Equip. Migration Plan" Tab
Migration and Consolidation (Level 4)
4-1 | Level 4A - If your Migration Plan for all Mission Critical Applications is complete, how are you performing against the schedule? | <select value>
4-2 | Level 4B - If you plan to close your data centers is complete, how are you performing against the schedule? | <select value and complete columns Q on the "Data Centers" tab>
4-3 | Enter any commentary regarding your progress (optional) | <enter text>
Completion (Level 5)
5-1 | Have you completely migrated all Mission Critical and Public Facing Applications? | <Select Yes or No>
5-2 | Have you completely closed all data centers? | <Select Yes or No>
Virtualization and Compression
V-1 | Do you plan to incorporate virtualizing servers into the consolidation/migration effort? | <enter value>
V-2 | If you plan to virtualize before migrating, have you started the initiative? | <select value> | <select value>
V-3 | If assessment is completed: |  | Have not started the initiative
V-3a | Total # of servers identified | <enter # of servers in your organization> | Started Assessment
V-3b | # of servers targeted for virtualization | <enter # of servers which are candidates for virtualization> | Completed Assessment
V-3c | What types of environments does your plan include? | <select a value> | Commenced Consolidation
V-4 | If consolidation has commenced: |  | Completed Consolidation
V-4a | Servers virtualized to date | <enter # of servers virtualized> | Not Started
V-4b | Current # of host virtualization (physical) servers | <enter # of physical servers>
V-5 | If virtualizing after migration, would assistance from the Technology Agency be valuable | <select value> | <select value>
Plan to lead and execute all departmental virtualization efforts,
Would prefer assistance from State personnel with experience with virtualization
Would prefer the effort be lead by State personnel with experience with virtualization

## MC-PF Applications
Mission Critical and Public Facing Inventory
Completed at End of Level 2 (Assessment) | [10 empty] | Completed at End of Level 3 (Planning)
# | Application Name | Application Type |  | Current Data Center Location |  | Current Inventory |  | Application's Target Location |  |  | Rack Mounted Space Required at Target Data Center |  | Other Floor Space Required at Target Data Center | Planned Migration Dates (for New Applications Enter Go-Live Date in End Date Field) |  | Notes
|  | Production, Disater Recovery | Description of Other | Technology Agency, Dept or New App. | Dept. Data Center | Total # of Racks/Cabinets | Total # of Physical Servers | Data Center | Name of Other Data Center | Justification for not moving the Application | # of Rack Units | # of Racks/Cabinets Required |  | Start Date | End Date
1 |  | <select value> | <Describe other type of Application (Pre-Prod etc.) | <select value> | <enter DC# from Data Center worksheet> | <enter # of racks/ cabinets currently at data center> | <enter # of physical servers currently at the data center> | <select value> |  | <enter value> | <enter # of rack units required to house physical servers> | <enter # of rack units required to house physical servers> | <enter floor space required for non-rack mounted equipment> | MM/YY | MM/YY
2 |  | <select value> |  | <select value> |  |  |  | <select value> |  | <enter value>
3 |  | <select value> |  | <select value> |  |  |  | <select value> |  | <enter value>
4 |  | <select value> |  | <select value> |  |  |  | <select value> |  | <enter value>
5 |  | <select value> |  | <select value> |  |  |  | <select value> |  | <enter value>
6 |  | <select value> |  | <select value> |  |  |  | <select value> |  | <enter value>
7 |  | <select value> |  | <select value> |  |  |  | <select value> |  | <enter value>
8 |  | <select value> |  | <select value> |  |  |  | <select value> |  | <enter value>
9 |  | <select value> |  | <select value> |  |  |  | <select value> |  | <enter value>
10 |  | <select value> |  | <select value> |  |  |  | <select value> |  | <enter value>
11 |  | <select value> |  | <select value> |  |  |  | <select value> |  | <enter value>
12
<if additional applications are identified after the first survey, please add at the bottom and highlight in red>
Note on B3: Bateman,Richard: Insert One row for each application instance (e.g. Production, Disaster Recovery)

## Data Centers
Data Center Inventory
Completed at End of Level 2 (Assessment) | [11 empty] | Completed at End of Level 3 (Planning) |  |  |  | Completed During Level 4 (Migration)
# | Data Center/Server Room Name | Address | Ownership |  | Primary Data Center Role |  |  |  | Size (sq. ft) | Current Inventory |  | Migration Dates |  | Projected Effort (person-days) | If Data Center will not close within the Technology Agency's timeline, enter Justification | Effort Remaining (person-days)
|  |  | Ownership | Other (describe) | Dev/ Test | Prod. | Disater Recovery | Other (describe) |  | Total # of Racks/Cabinets | Total # of Physical Servers | Start Date | End Date
1 |  |  | <enter value> | <if other, please explain> | <Enter X if used> | <Enter X if used> | <Enter X if used> |  | <size of data center> | <enter # of racks/ cabinets currently at data center, excluding MC/PF Applications> | <enter # of physical servers currently at the data center, excluding MC/PF Applications> | MM/YY | MM/YY | <enter budgeted person-days> |  | <enter effort remaining>
2 |  |  | <enter value>
3 |  |  | <enter value>
4 |  |  | <enter value>
5 |  |  | <enter value>
6 |  |  | <enter value>
7 |  |  | <enter value>
8 |  |  | <enter value>
9 |  |  | <enter value>
10 |  |  | <enter value>
11 |  |  | <enter value>
12
<insert more rows as needed>

## Equip. Migration Plan
Miscellaneous Applications Migration Plan Summary
Completed at End of Level 3 (Planning)
Quarter | OTech |  |  |  |  | Federated Data Center |  |  |  |  | Other Technology Agency Approved Tier 3 Data Center <ENTER NAME(S)>
| Rack-Mounted Servers |  |  | Non-rack mounted servers (rack/cabinet equivalent) | Stand-alone Storage Arrays (cabinet equivalent) | Rack-Mounted Servers |  |  | Non-rack mounted servers (cabinet equivalent) | Stand-alone Storage Arrays (cabinet equivalent) | Rack-Mounted Servers |  |  | Non-rack mounted servers (cabinet equivalent) | Stand-alone Storage Arrays (cabinet equivalent)
| # of Virtual Servers | # of Physical Servers | # of Racks/Cabinets |  |  | # of Virtual Servers | # of Physical Servers | # of Racks/Cabinets |  |  | # of Virtual Servers | # of Physical Servers | # of Racks/Cabinets
Q1, 2011 | <enter number> | <enter number> | <enter number> | <enter number> | <enter number> | <enter number> | <enter number> | <enter number> | <enter number> | <enter number> | <enter number> | <enter number> | <enter number> | <enter number> | <enter number>
Q2, 2011
Q3, 2011
Q4, 2011
Q1, 2012
Q2, 2012
Q3, 2012
Q4, 2012
Q1, 2013
Q2, 2013
Q3, 2013
Q4, 2013