## PM Maturity
Project Management Risk Assessment
Project Name:
Dept. of Tech. Project #:
Department:
Revision Date:
Low | Attribute | High | Rating | Required Stage
| Organization |  |  | Stage 1
Yes | Does the organization have a dedicated Project Management Office (PMO)? | No
Yes | Does the organization have well-defined project management processes? | No
Cooperative relationship | Business team and information technology (IT) team relationship | Adversarial relationship
Always | Staff uses established processes | Rarely or never
All | Of the projects in the past, how many project managers were state staff? | None
High | Staff commitment to the project | Low
High cohesiveness | Teamwork across the organization | Low cohesiveness
Impeccable record | History of delivering projects within budget/scope/schedule | Poor
None | Special Project reports (SPRs) in the past | Too many
None | History of suspended and/or terminated projects | Many
None | Negative or unaddressed report findings in the recent past by control/legislative/other entities | Many
None | Do past PIERs show any pattern of weakness? | Many
Regularly | Conducts regular project review meetings at all levels | None
High | Collaborative environment | Low
None | History of contract dispute ending in loss, contractor filing claims, contract termination due to dispute | Yes
Low | Tolerance to risk in this organization | High
Many | History of projects of similar size/complexity | None
| Governance |  |  | Stage 1
Well-defined | Does the organization have a project governance structure? | None
High | Executive representation in the governance structure | None
Well-defined | How well are the governance roles and responsibilities defined? | None
Always | Are there steering committees for all projects? | None
High | Sponsorship commitment to the project | Low
Yes | Are there well-defined escalation procedures in place? | None
High | Management team commitment to the project | Low
| Processes |  |  | Stage 1
Well-defined | Well-defined business processes and practices in place | No
Very well | How well does the organization's project management practices and processes meet PMBOK best practices? | Not at all
Yes | Is there a demonstrated and repeatable process in place? | No
Yes | Does the organization have well-defined project management deliverables? | No
Culture enforces review process | Are there well-defined review/gating processes in place? | No
Strong QA | Is there a well-defined quality assurance (QA) process in place? | No QA
Well-defined scope mgmt. process | Are there scope management processes and tools in place? | No
Well-defined risk mgmt. process | Are there risk management processes and tools in place? | No
Well-defined change mgmt. process | Are there change management processes in place? | No
Well-defined schedule mgmt. including Critical Path mgmt. | Are there schedule management processes in place? | No
Many | Number of projects in which the project management process has been used | None
Well-defined cost mgmt. process | Are there cost management processes in place? | No
Well-defined communication plan/proc. | Are there communication processes in place? | No
Well-defined configuration control | Are there configuration management processes and tools in place? | No
| Proposed Project Manager (PM) Capability |  |  | Stage 2
Seasoned | Proposed PM's experience | Novice
Impeccable record | Proposed PM's track record | Poor
Yes | Is the proposed PM PMP certified? | No
High | PM's experience with the business processes | None
High | PM's business domain knowledge | None
Yes | Does the PM have sufficient technical background/skills? | No
Yes | Have the sponsors assigned sufficient number of project management staff? | No
High | PM's commitment to the project | Low
Stage 1 Business Analysis - Project Management Risk Assessment Total: |  |  | 0 | Stage 1
Stage 1 Business Analysis - Project Management Risk Score: |  |  | 0
Stage 2 Alternatives Analysis - Project Management Risk Assessment Total: |  |  | 0 | Stage 2
Stage 2 Alternatives Analysis - Project Management Risk Score: |  |  | 0
0.0 0.5 1.0 1.5 2.0 2.5 3.0 3.5 4.0 5.0